# Milestone-Based Sprint Plan for Your GitHub Project Board

## Copy-ready milestone entries

Milestones are a good fit for sprint planning because they can group issues/PRs, carry a milestone description, show completion progress, and support filtering by milestone. [1]

Sprint cadence and dates (assumptions) - Dates are DD/MM/YYYY in 2026 - Workdays are Mon–Fri, no holidays - Standard sprint is 2 weeks (10 working days), but the fixed deadline requires a short final sprint: - 7 full sprints (14 calendar days each) - 1 release sprint (10 calendar days; 7 working days)

### Milestone: S1 — Foundations: Core Infra + Data Intake

Dates: 12/02/2026 → 25/02/2026
Milestone description (copy-ready): Establish a running baseline system with CI, containerized local environment, baseline routing, health checks, and initial data acquisition. This creates the minimum integrated foundation for telemetry and decision services to plug into.

Key deliverables (3–5) - Baseline runtime: load balancer + dummy backends + health checks (streams: integration, testing | epics: core-infra) - Repo hygiene: branching strategy + CI pipeline + minimal “Definition of Done” gates (streams: integration, deployment, testing | epics: core-infra) - Logging baseline and error visibility (streams: integration | epics: core-infra) - Workload trace dataset acquired + stored with defined schema/README (stream: data | epic: data-foundation) - Anomaly dataset acquired + curated sample subset for fast iteration (stream: data | epic: data-foundation)

Acceptance criteria - CI is green; unit tests execute on every PR; merge is blocked on failures - One-command local run starts the baseline system end-to-end - Baseline routing distributes requests; unhealthy backends are removed from rotation reliably - Data sources are accessible, documented, and reproducible (scripts or clear steps)

Depends on - None (project start)

Recommended role assignments - Platform/Integration Engineer: baseline routing, service scaffolding - DevOps/Release Engineer: CI pipeline, containerization, environment scripts - Data/ML Engineer: dataset acquisition, schema/metadata - QA/Test Engineer: unit tests, health-check tests, CI test gates - PM: scope control, acceptance sign-off, sprint ceremonies

### Milestone: S2 — Telemetry Baseline + Golden Dataset

Dates: 26/02/2026 → 11/03/2026
Milestone description (copy-ready): Instrument the running system and deliver an observability loop (collection → storage → dashboards). Produce a “golden dataset” subset and baseline evaluation harness so decision/ML work can progress without blocking.

Key deliverables (3–5) - End-to-end telemetry pipeline and dashboards (streams: integration, deployment | epic: telemetry) - Telemetry validation and synthetic load generator (streams: testing, integration | epic: telemetry) - Golden dataset: cleaned, versioned subset with reproducible preprocessing (streams: data, documentation | epic: data-foundation) - Baseline offline evaluation harness (streams: ml, testing | epic: decision-intelligence groundwork) - Telemetry schema + runbook draft (stream: documentation | epic: documentation)

Acceptance criteria - Metrics/traces/logs are visible for a sustained synthetic run and can be queried reliably - Dashboard includes at least: request rate, latency, error rate, backend health, routing distribution - Golden dataset generation is reproducible (scripted or documented deterministic steps) - Baseline evaluation runs end-to-end on the golden dataset without manual intervention

Depends on - S1 foundation: runnable services + CI + baseline routing

Recommended role assignments - Observability/Platform Engineer: instrumentation and telemetry pipeline - Data/ML Engineer: golden dataset, baseline metrics definitions - QA/Test Engineer: synthetic load + telemetry validation tests - DevOps/Release Engineer: telemetry deploy config and environment consistency - PM: milestone scope + acceptance review

### Milestone: S3 — Decision Intelligence v1: Anomaly-Driven Routing Constraints

Dates: 12/03/2026 → 25/03/2026
Milestone description (copy-ready): Deliver the first closed loop between detection and action: anomaly detection (v1) produces signals that enforce safe routing constraints. Include scenario replay and end-to-end tests proving behavior.

Key deliverables (3–5) - Anomaly detection service v1 + real-time signaling contract (streams: ml, decision | epic: decision-intelligence) - Routing constraints integrated into load balancer (streams: decision, integration | epic: decision-intelligence) - Scenario replay harness (streams: data, testing | epic: decision-intelligence) - End-to-end anomaly scenario test suite (stream: testing | epic: integration) - Decision contract and troubleshooting docs updated (stream: documentation | epic: documentation)

Acceptance criteria - When anomaly state is “degraded/unhealthy,” routing avoids affected backends within a defined response time - E2E anomaly tests pass in CI (at least one “happy path” + one “failure path”) - Safe fallback exists if anomaly service is unavailable (e.g., revert to health-check-only routing) - Telemetry captures detection events and routing changes end-to-end

Depends on - S2 telemetry baseline + golden dataset - S1 baseline routing + health checks

Recommended role assignments - ML Engineer: anomaly model/service implementation - Decision Engineer: routing policy constraints + thresholds - Platform/Integration Engineer: service wiring + contracts - QA/Test Engineer: E2E scenario tests + regression seed suite - PM: acceptance definition + stakeholder review

### Milestone: S4 — Forecasting + Autoscaling Control Loop

Dates: 26/03/2026 → 08/04/2026
Milestone description (copy-ready): Introduce forecasting and autoscaling into a controlled loop with explicit safety constraints. Demonstrate scale-up/scale-down under synthetic workload profiles and record outcomes via telemetry.

Key deliverables (3–5) - Forecasting microservice v1 (stream: ml | epic: autoscaling) - Autoscaling decision logic + cooldown/anti-thrashing constraints (stream: decision | epic: autoscaling) - Scaling integration (register/deregister capacity) (streams: integration, deployment | epic: autoscaling) - Load spike and steady-state scale tests (stream: testing | epic: integration) - Operator config + “disable autoscaling” procedure (stream: documentation | epic: documentation)

Acceptance criteria - Under sustained increase, system scales up within defined time; under sustained decrease, scales down safely - Safety constraints enforced: min/max, cooldowns, rollback/disable path - Telemetry records scaling events and impact (latency, errors, capacity changes) - Autoscaling can be toggled off without breaking baseline routing

Depends on - S2 telemetry baseline (inputs and observability) - S3 decision constraints (safety-first gating)

Recommended role assignments - ML Engineer: forecasting model/service - Decision Engineer: autoscaling policy, safety constraints - Platform/Integration Engineer: scaling hooks + capacity registry - DevOps/Release Engineer: runtime configuration + deployment toggles - QA/Test Engineer: load profiles + validation of scale behaviors

### Milestone: S5 — RL Routing: Feasibility to Shadow Integration

Dates: 09/04/2026 → 22/04/2026
Milestone description (copy-ready): Build RL routing feasibility with offline training and reproducible evaluation. Integrate RL recommendations in shadow mode (logged, not enforced) with strict policy gating and benchmarks vs baseline.

Key deliverables (3–5) - RL simulation environment + offline training pipeline (stream: ml | epic: rl-routing) - RL policy outputs and decision interface (stream: decision | epic: rl-routing) - Shadow mode integration (recommendations computed + logged) (streams: integration, deployment | epic: rl-routing) - Comparative benchmarks RL vs baseline (stream: testing | epic: integration) - Experiment notes + reproducibility instructions (stream: documentation | epic: documentation)

Acceptance criteria - RL training/eval is reproducible (seeded runs; artifacts stored; metrics comparable) - Shadow mode runs without impacting routing stability or availability - Benchmark report includes: latency, error rate, load distribution, and stability indicators - Explicit go/no-go criteria defined for any non-shadow enablement

Depends on - S1 baseline routing (baseline comparator) - S2 telemetry (measurement) - S3 routing constraints (safety guardrails) - S4 autoscaling constraints if RL interacts with capacity decisions

Recommended role assignments - ML Engineer: simulation + training + evaluation metrics - Decision Engineer: policy gating, fallback logic, “shadow vs active” design - Platform/Integration Engineer: runtime hook for shadow mode, logging/events - QA/Test Engineer: benchmarking harness + safety test cases - PM: scope guard (shadow-first), milestone sign-off

### Milestone: S6 — Integration Gates + Policy Manager + Benchmark Readiness

Dates: 23/04/2026 → 06/05/2026
Milestone description (copy-ready): Consolidate into a policy-driven integrated product with automated gates. Add policy manager, configuration validation, regression/performance/fault tolerance tests, and tune system based on measured results.

Key deliverables (3–5) - Policy manager controlling modes (baseline / anomaly constraints / autoscaling / RL shadow) (stream: integration | epic: integration) - Configuration validation + secure defaults (streams: deployment, integration | epic: integration) - Automated test suite: regression + performance + resilience (stream: testing | epic: integration) - Failure handling and fallback validation (streams: decision, testing | epic: integration) - Performance tuning iteration based on benchmark outputs (streams: integration, testing | epic: integration)

Acceptance criteria - CI “release gate” exists: build + unit + selected E2E + regression + baseline perf checks - System remains stable under defined failure injections (service down, telemetry disruption, backend failure) - Policy toggles work reliably and are documented (no hidden manual steps) - Benchmark methodology is consistent and repeatable

Depends on - S3–S5 implemented loops (anomaly, autoscaling, RL shadow)

Recommended role assignments - Platform/Integration Engineer: policy manager + integration hardening - QA/Test Engineer: test automation + resilience/performance suites - DevOps/Release Engineer: validated configs + release gating pipeline support - Decision Engineer: fallback semantics and safe-mode criteria - PM: acceptance criteria enforcement + release readiness tracking

### Milestone: S7 — Deployment Candidate + Documentation Completion

Dates: 07/05/2026 → 20/05/2026
Milestone description (copy-ready): Produce a release candidate suitable for demo/review: deployment packaging, defect burn-down, reproducible benchmarks, and near-final documentation (user guide + technical docs + report draft).

Key deliverables (3–5) - Demo/production-style deployment setup + release checklist (stream: deployment | epic: deployment) - Critical bugfixes + code cleanup/refactoring for stability (stream: integration | epic: integration) - Final benchmark runs + results reporting draft (streams: testing, documentation | epic: documentation) - User guide + technical documentation draft complete (stream: documentation | epic: documentation) - Demo script + presentation draft prepared (streams: documentation, deployment | epic: documentation)

Acceptance criteria - Fresh-environment deploy works using documented steps (repeatable by a reviewer) - No open critical/high-severity issues; known issues documented with workarounds - Benchmark report draft includes results + methodology + environment details - Demo run completes end-to-end using the release candidate build

Depends on - S6 integration gates and policy controls

Recommended role assignments - DevOps/Release Engineer: packaging, deploy checklist, environment readiness - QA/Test Engineer: benchmark runs, final regression preparation - Documentation Owner (Engineer): docs completion and report draft integration - Platform/Integration Engineer: critical fixes and stabilization - PM: final scope lock + demo readiness management

### Milestone: S8 — Final Delivery and Handoff

Dates: 21/05/2026 → 30/05/2026
Milestone description (copy-ready): Final hardening and delivery window. Run final acceptance tests, tag the release, finalize documentation and presentation, and deliver all artifacts by 30/05/2026.

Key deliverables (3–5) - Final release tag/package and artifact bundle (stream: deployment | epic: deployment) - Final regression + acceptance verification checklist (stream: testing | epic: integration) - Final report + slides + demo materials (stream: documentation | epic: documentation) - Dataset documentation/licensing appendix (streams: data, documentation | epics: data-foundation, documentation) - Buffer for critical-only fixes (stream: integration | epic: integration)

Acceptance criteria - Final acceptance checklist complete: tests green, deployment verified, demo verified, docs complete - Reproducibility validated from scratch (setup → run → reproduce results) - Final delivery artifacts packaged and stored in the agreed location - Only pre-approved known issues remain, with clear severity and workaround notes

Depends on - S7 release candidate

Recommended role assignments - Release Manager (DevOps/Release Engineer or Tech Lead): final packaging + tagging - QA/Test Lead: final validation + sign-off evidence - Documentation Lead: final report + slides + handoff checklist - PM: delivery coordination + final acceptance sign-off - Platform/Integration Engineer: critical fix responder (timeboxed)

## Executive summary

This plan creates 8 milestone-based sprints from 12/02/2026 to 30/05/2026, with seven 2-week sprints and a shortened final release sprint to meet the fixed deadline. The core design principle is parallelization by streams every sprint, rather than completing one module at a time: each sprint contains coordinated work across ml, decision, integration, testing, deployment, data, and documentation, so a 3–6 person team can proceed without serial bottlenecks.

A sprint is treated as a fixed-duration timebox once started, which is consistent with standard Scrum guidance (one month or less, fixed length). [2] The milestones are structured to match how GitHub milestones are commonly used: grouping issues and PRs under a due date and description and tracking completion. [3]

Epic priority is preserved by sequencing “must-exist foundations” first (data-foundation, core-infra, telemetry), then the decision layers (decision-intelligence → autoscaling → rl-routing), then hardening (integration), then packaging (deployment) and completion (documentation). The final sprint explicitly acts as a release/handoff buffer rather than feature expansion.

## Label set to create

Labels help categorize and find work across issues and PRs, and GitHub supports label name + description + hex color. [4]
Below is a clean, scalable label taxonomy matching your requested categories: stream:, epic:, type:.

### Stream labels

| Label name | Description (copy-ready) | Color |
| --- | --- | --- |
| stream:ml | Model development, training pipelines, evaluation, and inference services. | 2B6CB0 |
| stream:decision | Decision/policy logic (thresholds, constraints, autoscaling rules, RL gating, fallbacks). | 6B46C1 |
| stream:integration | Core services, routing, contracts, system wiring, policy manager, and cross-service integration. | 2F855A |
| stream:testing | Automated tests, load tests, benchmarks, fault tolerance/resilience testing, quality gates. | B7791F |
| stream:deployment | CI/CD release workflows, packaging, environment config, deployment automation, release tagging. | 2C7A7B |
| stream:data | Dataset acquisition, preprocessing, scenario generation, provenance, reproducibility of data pipelines. | 2C5282 |
| stream:documentation | User guides, technical docs, runbooks, reports, presentations, demo scripts. | 718096 |

### Epic labels

| Label name | Description (copy-ready) | Color |
| --- | --- | --- |
| epic:data-foundation | Datasets, preprocessing, provenance, and baseline data pipelines enabling downstream ML/decision work. | 1A365D |
| epic:telemetry | Instrumentation, collection, storage, dashboards, and telemetry validation used by decision loops. | 22543D |
| epic:core-infra | Repo foundations, baseline routing, health checks, service scaffolding, baseline reliability. | 744210 |
| epic:decision-intelligence | Anomaly detection and decision constraints that turn signals into safe routing actions. | 702459 |
| epic:autoscaling | Forecasting + scaling decisions + safety constraints and integration with capacity management. | 234E52 |
| epic:rl-routing | RL simulation/training, routing policy outputs, shadow/controlled rollout, and RL evaluation. | 2A4365 |
| epic:integration | Policy manager, end-to-end wiring, security/config validation, and integrated system behavior. | 276749 |
| epic:deployment | Release candidate build, packaged deployment, demo environment, release checklist, final delivery artifacts. | 285E61 |
| epic:documentation | User guide, technical documentation, benchmark report, final report, and presentation/demo materials. | 4A5568 |

### Type labels

| Label name | Description (copy-ready) | Color |
| --- | --- | --- |
| type:feature | New product capability (user-visible or system capability). | 3182CE |
| type:task | Implementation task that contributes directly to a feature or epic deliverable. | 38A169 |
| type:bug | Defect, unexpected behavior, or regression. | E53E3E |
| type:spike | Timeboxed research/prototype with documented findings (may be discarded). | D69E2E |
| type:refactor | No behavior change intended; improves structure, maintainability, or performance. | 805AD5 |
| type:test | Adds or improves automated tests, harnesses, benchmarks, or quality gates. | DD6B20 |
| type:docs | Documentation-only work (guides, runbooks, diagrams, reports). | 718096 |

Label usage rule (recommended) - Each issue gets exactly one stream:*, exactly one epic:*, and exactly one type:* - Each issue also belongs to exactly one sprint milestone (S1–S8) This makes filtering and milestone progress tracking straightforward. [5]

## Sprint-by-stream plan summary

The table below is the “parallelization contract”: every sprint includes meaningful work in multiple streams so the team is not forced into sequential module completion.

| Sprint (dates) | data | ml | decision | integration | testing | deployment | documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S1 (12/02–25/02) | Acquire workload + anomaly datasets; define schema | Define baseline evaluation plan + metrics | Define decision interfaces (signals/health states) | Baseline routing + health checks; service scaffolding | Unit tests + CI gates for routing/health | CI pipeline + env scripts foundation | Repo README + DoD + architecture sketch |
| S2 (26/02–11/03) | Golden dataset subset + preprocessing reproducibility | Baseline offline training/eval harness | Define thresholds + routing constraint semantics | Full telemetry pipeline + dashboards | Synthetic load + telemetry validation | Telemetry deploy config + env parity | Observability spec + runbook draft |
| S3 (12/03–25/03) | Scenario replay inputs for anomaly cases | Anomaly detection service v1 | Routing constraints driven by anomaly signals | Contracts + wiring + fallback path | E2E anomaly suite + regression seed | Demo compose/scripts updated | Decision API + troubleshooting docs |
| S4 (26/03–08/04) | Backtesting windows + forecasting-ready splits | Forecasting service v1 | Autoscaling policy + safety constraints | Scaling integration + control loop wiring | Load spike/scale tests | Autoscaling toggles + runtime configs | Autoscaling operator docs |
| S5 (09/04–22/04) | RL environment inputs + reproducibility artifacts | RL offline training + evaluation | RL gating + fallback hierarchy | Shadow integration of RL outputs | RL vs baseline benchmarks | Feature flags + rollback plan | Experiment notes + results interpretation |
| S6 (23/04–06/05) | Data provenance structure + retention notes | Final model selection inputs + quality dashboards | Safe-mode criteria + policy semantics | Policy manager + config validation | Full test suite (regression/perf/resilience) | Release-gate pipeline + RC packaging draft | Test plan + benchmark methodology docs |
| S7 (07/05–20/05) | Dataset licensing/attribution pack | Model export/freeze + final eval summary | Final policy defaults + sign-off | Stabilization fixes | Benchmark runs + results reporting | Deployment candidate + release checklist | User guide + technical docs + report draft |
| S8 (21/05–30/05) | Final data appendix | Artifact reproducibility notes | Parameter lock + final risk sign-off | Critical-only fixes buffer | Final regression + acceptance testing | Release tag + delivery packaging | Final report + slides + demo script + handoff |

## Dependencies and critical path

### Milestone dependency model

The sequencing below preserves your epic priority while keeping parallel work active each sprint.

flowchart LR
  S1[S1 Foundations] --> S2[S2 Telemetry baseline]
  S2 --> S3[S3 Anomaly-driven routing]
  S3 --> S4[S4 Forecasting + autoscaling]
  S4 --> S5[S5 RL shadow integration]
  S5 --> S6[S6 Integration gates + policy manager]
  S6 --> S7[S7 Deployment candidate]
  S7 --> S8[S8 Final delivery]

  DF[epic:data-foundation] --> S3
  DF --> S4
  DF --> S5
  TLM[epic:telemetry] --> S3
  TLM --> S4
  CI[epic:core-infra] --> S2

### Key task dependencies you should enforce on the board

To keep the board dependency-aware without over-complicating it, enforce these “gates”:

- Gate A (end of S1): runnable baseline system + CI gates + initial datasets
Enables telemetry instrumentation without blocking on infrastructure changes.

- Gate B (end of S2): telemetry loop + golden dataset subset
Enables decision services and model iteration with measurable outcomes.

- Gate C (end of S3): anomaly signals drive safe routing constraints + E2E tests
Establishes safety mechanisms that must exist before automation expands.

- Gate D (end of S4): autoscaling loop with safety constraints + load tests
Prevents thrashing/unstable scale behavior before RL experiments expand.

- Gate E (end of S6): policy manager + automated quality gates
Required before release candidate packaging is considered valid.

- Gate F (end of S7): deployable release candidate + docs draft complete
Required to enter final delivery sprint without feature creep.

Milestones and issues can be filtered and tracked using milestone association and milestone search syntax, helping you continuously validate that dependent work is flowing into the current sprint. [6]

## Roles and ownership model

A 4-engineer + 1 PM structure can cover all streams in parallel each sprint:

- Platform/Integration Engineer: owns the running system, contracts, routing, policy manager, and “wiring”

- ML Engineer: owns modeling services, training/evaluation, reproducibility of ML artifacts

- Decision Engineer (can be same as ML or Platform depending on team): owns policy logic, thresholds, constraints, safe modes, rollbacks

- QA/Test Engineer (or engineer wearing QA hat): owns automated suites, benchmarks, failure injection, regression gates

- PM (or Tech Lead acting as PM-lite): owns milestone scope, acceptance criteria, risk management, delivery readiness

Labeling and milestone discipline matter because GitHub labels and milestones are intended to categorize and track work across issues/PRs, and consistency improves discoverability and reporting. [7]

## Risks and mitigations

Risk: Sequential “module-by-module” execution sneaks back in
Mitigation: enforce the sprint-by-stream table as a weekly check; each sprint must have active issues in at least 4 streams before sprint start.

Risk: ML work blocks on telemetry availability
Mitigation: keep golden datasets and offline harnesses in S2; treat live telemetry consumption as a separate integration task so ML iteration continues even if telemetry is imperfect.

Risk: RL scope threatens the deadline
Mitigation: keep RL in shadow mode through S5–S7; require explicit go/no-go criteria and policy gating before any active enforcement.

Risk: Testing deferred until late causes integration collapse
Mitigation: begin with unit tests and CI gates in S1, telemetry validation in S2, E2E scenario tests in S3–S4, and full gate suite in S6.

Risk: Release sprint becomes feature sprint
Mitigation: S8 is explicitly “critical fixes only.” If new features appear, they must be deferred unless they unblock delivery acceptance criteria.

Risk: Documentation is left to the end
Mitigation: require a doc deliverable every sprint (runbook updates, interface docs, experiment notes) so S7–S8 are consolidation, not creation-from-scratch.

## Timeline and final delivery milestone

### Gantt-style timeline

gantt
  title Sprint Milestones (12/02/2026–30/05/2026)
  dateFormat  YYYY-MM-DD
  axisFormat  %d/%m

  section Sprints
  S1 Foundations                          :s1, 2026-02-12, 2026-02-25
  S2 Telemetry + golden dataset           :s2, 2026-02-26, 2026-03-11
  S3 Anomaly-driven routing constraints   :s3, 2026-03-12, 2026-03-25
  S4 Forecasting + autoscaling loop       :s4, 2026-03-26, 2026-04-08
  S5 RL feasibility + shadow integration  :s5, 2026-04-09, 2026-04-22
  S6 Policy manager + integration gates   :s6, 2026-04-23, 2026-05-06
  S7 Deployment candidate + docs draft    :s7, 2026-05-07, 2026-05-20
  S8 Final delivery                       :s8, 2026-05-21, 2026-05-30

  section Epic emphasis (overlapping)
  data-foundation     :df, 2026-02-12, 2026-05-20
  core-infra          :ci, 2026-02-12, 2026-03-11
  telemetry           :tlm, 2026-02-26, 2026-03-25
  decision-intelligence:di, 2026-03-12, 2026-04-08
  autoscaling         :aut, 2026-03-26, 2026-04-22
  rl-routing          :rl, 2026-04-09, 2026-05-06
  integration         :int, 2026-03-12, 2026-05-06
  deployment          :dep, 2026-05-07, 2026-05-30
  documentation       :doc, 2026-02-12, 2026-05-30

### Final delivery milestone checklist

For S8 (Final delivery and handoff), treat the checklist as “release gates”:

- Build and quality

- Final CI pass (unit + regression + required E2E)

- Final performance baseline run recorded

- Deploy and demo

- Fresh-environment deploy verified using the release checklist

- Demo script executed successfully using final artifacts

- Documentation

- Final report + user guide + technical docs complete and consistent with the delivered build

- Benchmark methodology and results included

- Artifacts and reproducibility

- Model artifacts and datasets/provenance notes included

- Steps to reproduce key results validated end-to-end

[1] [3] About milestones - GitHub Docs

https://docs.github.com/articles/about-milestones?utm_source=chatgpt.com

[2] The Scrum Guide™

https://scrumguides.org/docs/scrumguide/v2017/2017-Scrum-Guide-US.pdf?utm_source=chatgpt.com

[4] [7] Managing labels - GitHub Docs

https://docs.github.com/articles/labeling-issues-and-pull-requests?utm_source=chatgpt.com

[5] Filtering issues and pull requests by milestone - GitHub Docs

https://docs.github.com/issues/using-labels-and-milestones-to-track-work/filtering-issues-and-pull-requests-by-milestone?utm_source=chatgpt.com

[6] Associating milestones with issues and pull requests - GitHub Docs

https://docs.github.com/articles/associating-milestones-with-issues-and-pull-requests?utm_source=chatgpt.com