# Milestone-Based Sprint Plan for a SmartLoad GitHub Board

## Executive summary

This plan translates your prioritized epic labels—epic:data-foundation → epic:telemetry → epic:core-infra → epic:decision-intelligence → epic:autoscaling → epic:rl-routing → epic:integration → epic:deployment → epic:documentation—into a milestone-based sprint schedule from 12/02 to 30/05 (DD/MM), built for a 3–6 person cross-functional team (assumption: 4 engineers + 1 PM) and optimized for parallel work across streams every sprint (ML, decision, integration, testing, deployment, data, documentation).

Key outcomes of the structure:

- 8 milestones (sprints) total:

- 7 standard 2-week sprints (10 working days each)

- 1 shortened release sprint (to meet the fixed deadline)

- Every sprint contains work in at least 4 streams (often 6–7), so the team is never blocked into a “module-by-module” sequence.

- Milestones are designed around vertical slices: each sprint produces an integrated increment (running system + measurable/observable behavior + tests + documentation updates).

- The plan explicitly manages dependencies so that later epics (autoscaling, RL) are not started “in isolation,” but in parallel with integration/testing hardening and documentation maturity.

## Planning assumptions and working model

The dates and sprint geometry are fixed by your request:

- Start: 12/02 (assume 12 Feb 2026)

- Final delivery milestone: 30/05 (assume 30 May 2026)

- Workdays: Monday–Friday; no holidays

- Sprint length: 2 weeks unless schedule requires adjustment

- Because 12/02 → 30/05 is not an exact multiple of 2 weeks, the plan uses:

- Sprints 1–7: full two-week cadence

- Sprint 8: shorter “release/hardening” sprint to land exactly on 30/05

Operational model (how to implement this on your GitHub board):

- Milestones = sprints. Each issue belongs to one sprint milestone.

- Each issue carries:

- exactly one stream label: ml, decision, integration, testing, deployment, data, documentation

- exactly one epic label: epic:data-foundation, epic:telemetry, etc.

- Each sprint milestone has:

- a milestone definition (goal, scope boundaries),

- a deliverable checklist (what must exist at sprint end),

- acceptance criteria (objective evidence of completion),

- known dependencies/risks.

Tooling assumptions (kept intentionally lightweight, but compatible with your roadmap epics):

- Containerized development and consistent local orchestration (e.g., via Docker).

- Telemetry standardized through OpenTelemetry.

- Simple control-bus/comms (e.g., Redis pub/sub) where needed.

## Sprint calendar and milestone definitions

Sprint boundaries below follow your exact start and final end date. Note that the start is a Thursday, so the cadence runs Thu→Wed for full sprints, and the final delivery is a Saturday (30/05). Practically, you can treat Fri 29/05 as “engineering freeze” and Sat 30/05 as “submission/sign-off.”

| Sprint milestone | Start | End | Working days | Milestone name | Primary epic focus (priority order preserved) |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | 12/02 | 25/02 | 10 | Foundations and baseline routing | core-infra + data-foundation |
| Sprint 2 | 26/02 | 11/03 | 10 | Telemetry baseline and observability loop | telemetry (+ continued data/documentation) |
| Sprint 3 | 12/03 | 25/03 | 10 | Decision intelligence v1 | decision-intelligence (anomaly) + integration + testing |
| Sprint 4 | 26/03 | 08/04 | 10 | Forecasting and autoscaling loop | autoscaling + decision-intelligence + testing |
| Sprint 5 | 09/04 | 22/04 | 10 | RL routing experiments to controlled integration | rl-routing + integration + testing |
| Sprint 6 | 23/04 | 06/05 | 10 | System integration gates and benchmark readiness | integration + testing (+ policy controls) |
| Sprint 7 | 07/05 | 20/05 | 10 | Deployment candidate and documentation completeness | deployment + documentation (+ outcomes reporting) |
| Sprint 8 | 21/05 | 30/05 | 7 | Final delivery and handoff | final release + demo + final report |

## Sprint-by-sprint deliverables and acceptance criteria

The goal is to keep each sprint “balanced” so multiple engineers can work independently without waiting for an entire module to finish. Each sprint below includes deliverables by stream, milestone acceptance criteria, milestone dependencies, recommended roles, and risks/mitigations.

### Sprint deliverables table by stream

This is the “at-a-glance” sprint allocation that ensures parallel work. Each cell represents the minimum that should be inside the milestone.

| Sprint | data | ml | decision | integration | testing | deployment | documentation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Acquire workload + anomaly datasets; define data formats | Define baseline feature plan; stub training pipeline skeleton | Define “decision layer” interfaces (signals/contracts only) | Repo + CI; containerized local stack; baseline load balancer + dummy backends + health checks | Unit tests for routing + health checks; CI gates | Define deploy target (local demo first); draft release approach | Architecture overview; contribution guide; sprint “Definition of Done” |
| Sprint 2 | Clean/standardize datasets; create a small “golden subset” for fast iteration | First offline baselines on subsets; establish metrics (RMSE/MAPE, anomaly precision/recall) | Define anomaly thresholds + health states; control signal schema | Telemetry pipeline + instrumentation + dashboard; metrics storage wiring | Telemetry validation tests; synthetic load scripts | Environment config templates; telemetry in deploy config | Observability spec; runbook draft; telemetry schema docs |
| Sprint 3 | Dataset-derived anomaly scenarios; replay format for pseudo-live testing | Build anomaly detection microservice v1 | Failure-aware routing constraints integrated; anomaly signaling | Control bus wiring; service-to-service contracts; LB consumes anomaly signals | End-to-end anomaly scenario tests; regression suite “seed” | Compose files updated for all services; repeatable demo script v1 | Decision layer docs; API/contract docs; troubleshooting notes |
| Sprint 4 | Time-series windows + backtesting datasets for forecasting | Forecasting microservice v1 + model upgrade path | Autoscaling logic + safety constraints | Scaling integration (spawn/terminate instances); full control loop integration | Load spike tests + scale up/down tests; acceptance tests for stability | “Demo deployment” with autoscaling toggles; config defaults | Autoscaling policy doc; user-facing “how to run” update |
| Sprint 5 | RL simulation inputs; environment reproducibility artifacts | RL engine prototype + offline training + evaluation | Decision hierarchy (constraints → RL → fallback); shadow mode outputs | Integrate RL engine in shadow; enable/disable gates | Benchmark RL vs baseline; safety tests; performance profiling | Deploy “shadow RL” build; feature flags; roll-back plan | RL experiment report outline; results interpretation guidance |
| Sprint 6 | Data retention + dataset provenance structure | Final model selection; metric dashboards for model quality | Policy setpoints + safe modes validated | Policy manager + security/config validation; cross-module integration | Automated test suite; regression/performance/fault tolerance; tuning loop | Release candidate packaging; deploy checklist; monitoring bundle | Test plan docs; benchmark methodology; updated operator runbook |
| Sprint 7 | Dataset licensing + attribution pack | Final model export/freeze; final evaluation summary | Finalize decision policies; “safe mode” defaults | Hardening fixes; integration polish | Results reporting; final benchmark runs; failure drills | Production/demo deployment setup; release notes draft | Documentation completion: user guide, technical docs, final report draft |
| Sprint 8 | Final data appendix and citations (if required) | Deliver trained artifacts + reproducibility notes | Final parameter lock + risk sign-off | Critical bugfix buffer only | Final regression pass; release acceptance testing | Final release tag; final demo environment; submission packaging | Final report + presentation + demo script; handoff checklist |

### Milestone acceptance criteria by sprint

To keep acceptance objective and board-friendly, each sprint milestone should close only when these criteria are true.

Sprint 1 acceptance criteria (Foundation increment) - Main branch builds green on CI; local environment runs from a single command (compose/script). - Baseline routing works deterministically (e.g., round-robin) and health checks remove failing backends. - Data acquisition is complete enough to support baseline training (at minimum, one workload dataset + one anomaly dataset). - Unit tests exist for core routing behavior and run in CI. - Documentation exists for repo structure and development workflow.

Sprint 2 acceptance criteria (Telemetry loop increment) - Telemetry is produced, collected, stored, and visualized end-to-end. - Synthetic load can be generated and the resulting metrics are visible and queryable. - A “golden subset” dataset is produced for fast ML iteration. - Baseline offline models run on the subset and output measurable metrics. - Telemetry schema and runbook are updated and reviewed.

Sprint 3 acceptance criteria (Anomaly-driven decision increment) - Anomaly detection service produces health state outputs that can be consumed by the system. - Load balancer / routing component enforces constraints on unhealthy/degraded nodes. - Anomaly scenarios can be replayed and validated with end-to-end tests. - Shadow logs/telemetry confirm that mitigation triggers within defined monitoring intervals. - Deployment scripts/config reflect the additional services and can run the full demo locally.

Sprint 4 acceptance criteria (Autoscaling control loop increment) - Forecasting produces predictions on a schedule using stored telemetry/history. - Autoscaler consumes predictions and triggers scale actions; scaling infrastructure updates the backend pool. - Safety constraints exist (min/max instances, cool-downs, anti-thrashing measures). - Load spike tests demonstrate successful scale-up, and sustained low load demonstrates safe scale-down. - Operator-facing documentation describes how to run autoscaling and how to disable it safely.

Sprint 5 acceptance criteria (RL feasibility increment) - RL simulation environment is reproducible and can run training episodes. - RL engine trains offline and shows measurable improvement or at least stable behavior vs baseline in defined scenarios. - Shadow deployment runs: RL recommendations are computed and logged without affecting live routing. - Decision hierarchy is implemented (constraints first, RL second, fallback always available). - Evaluation/benchmark results are documented clearly enough for stakeholders to interpret.

Sprint 6 acceptance criteria (Integration gate increment) - Policy manager (or centralized policy mechanism) controls operating modes and safe fallbacks. - System passes automated test suite: unit, integration, regression, baseline performance checks. - Fault tolerance tests exist with documented outcomes and at least one mitigation improvement landed. - Deployment packaging is release-candidate quality (versioned images/artifacts, configs, repeatable steps). - Documentation includes test plans, benchmark methodology, and operator runbook updates.

Sprint 7 acceptance criteria (Release candidate increment) - Demo deployment achieves “one-click run” for reviewers (local or target environment). - Final benchmark runs are executed and results captured in a consistent report format. - Documentation is nearly complete: user guide + technical docs + report draft. - Codebase is cleaned and stabilized; any non-critical backlog is triaged.

Sprint 8 acceptance criteria (Final delivery milestone) - Final release tag/package created; demo environment validated using the final checklist. - Final regression test pass completed; only approved known issues remain (documented). - Final report + presentation + demo script finalized; handoff contents packaged. - Delivery completed on or before 30/05 (engineering freeze by 29/05 recommended).

## Dependencies and critical path

A dependency-aware plan should make the critical path obvious so you can protect it when scope pressure hits.

### Milestone dependency map

flowchart LR
  DF[epic:data-foundation\n(datasets + baselines)] --> DI1[Decision intelligence v1\n(anomaly + constraints)]
  CI[epic:core-infra\n(routing + services)] --> TLM[epic:telemetry\n(metrics loop)]
  TLM --> DI1
  DF --> AUT[epic:autoscaling\n(forecast + scale loop)]
  TLM --> AUT
  DI1 --> RL[epic:rl-routing\n(sim + shadow + safe integration)]
  AUT --> RL
  RL --> INT[epic:integration\n(policy + E2E gates)]
  INT --> DEP[epic:deployment\n(release candidate)]
  DEP --> DOC[epic:documentation\n(final deliverables)]
  DOC --> FINAL[Final delivery\n(30/05)]

### Practical task-level dependency rules

These “rules of engagement” help avoid deadlocks while keeping parallel work:

- Telemetry must precede ML services that consume live metrics, but data work and offline training can proceed in parallel earlier.

- Health constraints should precede optimization: anomaly-based constraints should gate RL and autoscaling actions (safety first).

- Policy/safe-mode controls must exist before enabling impactful automation (autoscaling/RL “active” modes).

- Testing and documentation are continuous, but Sprint 6–8 are the “quality ramp” where you prioritize stability and reproducibility over net-new features.

### Critical path to protect

In this timeline, the critical path is typically:

core-infra → telemetry → anomaly constraints → autoscaling loop → RL shadow + evaluation → policy & E2E gates → deployment candidate → final docs/demo

When schedule pressure happens, the safest scope reductions are:

- reduce RL from “active routing” to shadow + evaluation only,

- keep autoscaling but simplify to conservative rules,

- keep anomaly detection to a stable baseline model (avoid over-optimizing model complexity),

- defer optional UI/dashboards if not required for demo acceptance.

## Roles, capacity, and risk management

### Recommended assignees by role (no specific people)

For a typical 4 engineers + 1 PM team, a workable assignment model is:

- Engineer A: Platform/Integration Engineer
Owns core services, routing changes, control-bus integration, cross-service contracts.

- Engineer B: Observability/Infrastructure Engineer
Owns telemetry pipeline, reliability, performance tuning, release packaging support.

- Engineer C: ML/Decision Engineer
Owns anomaly + forecasting + RL modeling, training code, offline evaluation.

- Engineer D: QA/Test Automation Engineer (or Full-stack engineer wearing QA hat)
Owns automated suite, regression gates, load testing, benchmarking harnesses.

- PM (or Tech Lead acting as PM-lite)
Owns milestones, scope control, acceptance sign-off, release checklist, documentation coordination.

If the team is closer to 3 engineers, merge roles as: - Integration+Infra combined, and QA automation becomes a shared responsibility with “test owner of the sprint.”

### Key risks and mitigations

Risk: ML work blocks on telemetry availability
Mitigation: enforce a “golden subset” dataset by Sprint 2 and keep offline baselines moving in parallel; treat live telemetry consumption as integration work, not the start of modeling.

Risk: RL scope expands and destabilizes delivery
Mitigation: make RL shadow mode the default; require policy gating and hard fallback; define a “minimum RL milestone” as evaluation + shadow logs.

Risk: Testing debt accumulates until the end
Mitigation: automated tests begin Sprint 1 (unit), expand Sprint 2 (telemetry validation), and formalize the quality ramp Sprint 6 onward.

Risk: Integration surprises (interfaces drift)
Mitigation: contracts/specs are treated as artifacts (docs + versioned schemas); add “contract test” checks early (Sprint 2–3).

Risk: Deployment environment complexity
Mitigation: one canonical demo environment first (containerized/local); any cloud deployment is optional and introduced only after release candidate stability.

Risk: Documentation becomes last-minute
Mitigation: every sprint produces a doc increment (runbook, schema doc, experiment notes); Sprint 7–8 are for consolidation, not starting from zero.

## Final delivery milestone

### Final delivery milestone definition

Milestone name: Final delivery and handoff
Date: 30/05 (recommended freeze by 29/05)
Goal: deliver a stable, demo-ready system with reproducible experiments, documented operation, and complete written deliverables.

### Final delivery checklist

- Release package

- Versioned tag/release; packaged artifacts and configs

- Demo environment validated from scratch (fresh machine/container pull)

- Quality and evidence

- Final regression test run recorded

- Benchmark results included (performance + resilience + model-quality)

- Documentation

- User guide

- Technical documentation (architecture + interfaces + runbook)

- Final report

- Slide deck + demo script

- Operations

- Clear “safe mode” settings and rollback instructions

- Known issues list with severity and workaround

### Gantt-style timeline

gantt
  title Milestone Timeline (12/02–30/05, DD/MM assumed, year 2026)
  dateFormat  YYYY-MM-DD
  axisFormat  %d/%m

  section Sprints (Milestones)
  Sprint 1: Foundations and baseline routing      :s1, 2026-02-12, 2026-02-25
  Sprint 2: Telemetry baseline and observability :s2, 2026-02-26, 2026-03-11
  Sprint 3: Decision intelligence v1             :s3, 2026-03-12, 2026-03-25
  Sprint 4: Forecasting and autoscaling loop     :s4, 2026-03-26, 2026-04-08
  Sprint 5: RL feasibility + shadow integration  :s5, 2026-04-09, 2026-04-22
  Sprint 6: Integration gates + benchmarking     :s6, 2026-04-23, 2026-05-06
  Sprint 7: Release candidate + docs draft       :s7, 2026-05-07, 2026-05-20
  Sprint 8: Final delivery and handoff           :s8, 2026-05-21, 2026-05-30

  section Epic focus windows (overlapping by design)
  epic:data-foundation     :df, 2026-02-12, 2026-05-20
  epic:core-infra           :ci, 2026-02-12, 2026-03-25
  epic:telemetry            :tlm, 2026-02-26, 2026-03-25
  epic:decision-intelligence:di, 2026-03-12, 2026-04-22
  epic:autoscaling          :aut, 2026-03-26, 2026-04-08
  epic:rl-routing           :rl, 2026-04-09, 2026-05-06
  epic:integration          :int, 2026-03-12, 2026-05-06
  epic:deployment           :dep, 2026-05-07, 2026-05-30
  epic:documentation        :doc, 2026-02-12, 2026-05-30